## Form Responses 1
Timestamp | Untitled Question

## Sheet1
Activity No. | Activity | Predecessor | Duration(In Days)
1 | Meeting With Client | - | 1
2 | Determine Scope and Goal of the Project | Meeting with Client | 3
3 | Determine Functionalities | Meeting with Client | 3
4 | Determine I/O's | Meeting with Client | 2
5 | Risk Analysis | Determine Scope and Goal of Project, Determine Functionalities | 2 |  |  | Determine Scope and Goal of the project | Risk Analysis | Project Size Estimation |  | FrontEnd Implementation
6 | Technical Practicality | Determine Functionalities | 2 |  |  | 3 | 2 | 2 |  | 7
7 | Project Size Estimation | Risk Analysis | 2 | [5 empty] | Model Design/System Design |  | Integration | Testing | Deployment/Deliver | End
8 | Cost and Time Estimation | Risk Analysis, Technical Practicality | 2 | [5 empty] | 5 |  | 3 | 2 | 1
9 | Model/System Design | Project Size Estimation, Cost and Time Estimation | 5 | Start | Meeting with Client | Determine functionalities | Technical practicality | Cost and Time Estimation |  | Backend Implementation
10 | FrontEnd Implementation | Model/System Design | 7 |  | 1 | 3 | 2 | 2 |  | 9
11 | BackEnd Implementation | Model/System Design | 9
12 | Integration | FrontEnd Implementation, BackEnd Implementation | 3
13 | Testing | Integration | 2 |  |  | Determine I/O's
14 | Deployment/Deliver | Testing | 1 |  |  | 2
| Critical Paths | Duration(In days)
| 1->2->5->7->9->11->12->13->14 | 28
| 1->2->5->8->9->11->12->13->14 | 28
| 1->3->5->7->9->11->12->13->14 | 28
| 1->3->5->8->9->11->12->13->14 | 28
| 1->3->6->8->9->11->12->13->14 | 28